## Sheet1
Project Name: On-Line Library Application
Test Script Name: |  | Sign onto App, Search for and Check out a book
Scenario/Purpose: |  | Determine if the application functions as expected
Prerequisites: |  | User is given sign on credentials for successful sign on
Name of Tester: |  | Jane Smith | Date: |  |  | 2019-11-12
|  |  | Time: |  |  | 4:20pm
Step | Description | Expected Results | Pass | Fail | N/A | Defect/Comments
1 | Enter loggin Credentials | Systems Log in user and displays menu | X
2 | Select search for a book | System opens book search menu | x
3 | Search for book by provided Id # B067312 | System displays availablity of book | x
4 | If book is available, Check out Book | Systems Checks out the book and return user to main menu | x
5 | Select search for book with criteria of your choosing | System Displays a list of books that meet criteria |  | x |  | System found no books and displayed message but did not return user to a subsequent menu
6 | If book is available, Check out Book | Systems Checks out the book and return user to main menu |  | X |  | Previous fail made it impossilbe to continue without restarting the app
7 | Select Exit the System from the menu | System Exits |  | X |  | Previous fail made it impossilbe to continue without restarting the app